## Gantt chart
[6 empty] | March 2025 | [14 empty] | April 2025 | [29 empty] | May 2025 | [30 empty] | June 2025 | [29 empty] | July 2025 | [30 empty] | August 2025
Workstream | Task | Team | Duration | Start Date | End Date | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Planning
| Conduct project kickoff meeting and finalize project specifications. | Product Manager | 2 | 2025-03-17 | 2025-03-18
Requirement Analysis
| Gather and document user requirements and design specifications. | Product Manager | 5 | 2025-03-19 | 2025-03-25
Design
| Create wireframes and prototypes for the user interface. | Frontend Developer | 4 | 2025-03-26 | 2025-03-31
Development
| Define and set up the backend architecture for RSS feed aggregation. | Backend Developer | 6 | 2025-03-26 | 2025-04-02
| Develop the frontend user interface for browsing and managing feeds. | Frontend Developer | 7 | 2025-04-01 | 2025-04-09
| Implement secure user authentication and account management features. | Backend Developer | 5 | 2025-04-03 | 2025-04-09
Integration
| Integrate frontend and backend components to ensure seamless operation. | Frontend Developer | 3 | 2025-04-10 | 2025-04-14
Testing
| Conduct unit testing for both frontend and backend components. | QA Engineer / DevOps | 4 | 2025-04-15 | 2025-04-18
| Perform integration testing to ensure all components work together. | QA Engineer / DevOps | 3 | 2025-04-21 | 2025-04-23
| Conduct user acceptance testing and gather final feedback. | QA Engineer / DevOps | 5 | 2025-05-05 | 2025-05-09
Review
| Gather feedback from stakeholders and conduct review sessions. | Product Manager | 2 | 2025-04-24 | 2025-04-25
| Plan and execute post-launch performance reviews and optimization. | Product Manager | 3 | 2025-05-20 | 2025-05-22
Deployment
| Deploy the application to a staging environment for further testing. | QA Engineer / DevOps | 2 | 2025-04-28 | 2025-04-29
| Launch the web application and monitor initial performance. | QA Engineer / DevOps | 2 | 2025-05-16 | 2025-05-19
DevOps
| Implement CI/CD pipelines for automated deployment and monitoring. | QA Engineer / DevOps | 3 | 2025-04-30 | 2025-05-02
Documentation
| Prepare and document project deliverables and user guides. | Product Manager | 4 | 2025-05-12 | 2025-05-15

## Human Resources
Role | Responsibilities | Estimated Hours/Week
Project Manager | Planning, coordination, documentation, stakeholder communication | 30-40
Backend Developer | API development, database management, authentication, feed aggregation | 30-40
Frontend Developer | UI/UX development, integration with backend, responsiveness | 30-40
QA/DevOps Developer | Testing, CI/CD, infrastructure management, performance monitoring | 30-40

## Tech Resources
Resource Type | Technology Used | Purpose
Backend Framework | C# / ASP.NET Core | API development
Frontend Framework | Razor Pages / Bootstrap | UI implementation
Testing | Xunit / Nunit | Unit testing
Database | PostgreSQL | Storing user data, feeds
Cloud Provider | Oracle Cloud | Hosting, scalability
Authentication | ASP.NET Core Identity | Secure user login
CI/CD Tools | GitHub Actions | Automated deployment
Monitoring | Prometheus / Grafana | Performance tracking
Other tools | StyleCop | Code quality analysis

## Financial Resources
Expense Category | Estimated Cost (USD) / Month | Description
Developer Salaries | 20000 | Based on market rates
Cloud Services | 500 | Hosting and database services
Third-party APIs | 200 | RSS parsing, authentication APIs
DevOps & Monitoring Tools | 300 | Logging, monitoring, CI/CD tools
Miscellaneous | 500 | Domain, legal, unexpected costs
Total Estimate (3 Months) | 64500